## Sheet2
Activity Plan (for lift and shift) | Time Required | Status | Remarks
1. Import data and explore | 0.5 Day | Done | Import and Exploring of Data in Python using Pandas, Numpy and Sqllite3 has been done
2. Create a model in python (jupyter notebook) | 1 Day | Done | The models are achieving AUC of 0.99+, on both training and OOT data during prediction. This could be a cause of Class Imbalance which may require R&D and Data Resampling for improvements.
a. Create derived variables using sql |  |  | Dynamic SQL & feature logic in Code A. 1. Target Distribution for Data Imbalance Check. 2. Data Filtering based on check of common anomalies. 3. Missing Values in records. 4. Numeric Summary, for deciding whether to choose log transform or not. 5. Segmentation of NTB Vs Existing Customers, checking importance of features in datasets. 6. Check for High FOIR Customers, checking importance of features in datasets.
b. Build about 3 to 4 models to test which one fits best |  |  | Logistic, DT, RF, XGB, LGBM all trained.
c. Select the best model to move to the next stage |  |  | Automated AUC-based selection
3. Divide the code into 2 parts | 0.5 Day | Done
a. Code for ETL and Derived variables (Code A) |  |  | code saved in code_A_data_prep.py
b. Code for the best model (Code B) |  |  | code saved in code_B_model_score.py
4. Save the training data and validation data in single store | 1 Day | Pending
Sample the validation data into 4 samples each of 25K |  | Done
Save the samples with the names |  | Done
HDFC_OOO_1_Q1 ¦ HDFC_OOO_2_Q2 ¦ HDFC_OOO_3_Q3 ¦ HDFC_OOO_4_Q4
5. Convert the Code A from sql to proc sql code (SAS Code C) | 2-3 Day | Pending
Covert the best model Code B to a .py file. |  | In Progress
Add the swat package to the end of the code to register the selected model to model manager and save it to GIT. (.py code D) |  | Pending
6. Create a flow in SAS studio as : SAS Code C à .py code D | 1-2 Day | Pending
7. In model manager, perform out of time validation and documentation of all the metrics requested in the excel shared | 2-3 Day | Pending
8. Using workflow manager set alerts for model decay and retraining workflow | 1-2 Day | Pending